## Requirement Traceability Matrix
Requirement ID | Phase | Module | Task | Description | Status | Assigned to
Req-101 | Requirment Gathering |  | Requirement Gathering | Collect the information required for the Tool | Completed | Sai Sindhu
Req-102 |  |  | Generate the necessary document templates | Create the requirement document for the development | Completed | Sai Sindhu
Req-103 | Analysis |  | Analyse the requirement and preare the necessary documents | Generate the feasibility Report for individual requirement. | Completed | Sai Sindhu
Req-104 |  |  |  | Priortise the requirement and create the matrix for the same. | Completed | Sai Sindhu
Req-105 | Design | System Design | Architecture for the tool | Finalise the Architecture for the tool | Completed | Sai Sindhu
Req-106 |  |  | Hardware/software finalization | Finalise the hardware and software required for the completion of project. | Completed | Sai Sindhu
Req-107 |  |  | Wire-Frame for web | Draw wireframe for the web-design | Completed | Sai Sindhu
Req-108 |  |  | Feasibility Check | Check the feasibility of develoment of requirement with base model | Completed | Sai Sindhu
Req-109 | Development | UI Development | UI Development for tool | Develop UI Interface for Preliminary Analysis | Completed | Chanabasagouda PATIL
Req-110 |  |  |  | Develop UI Interface for Detailed Analysis | Completed | Chanabasagouda PATIL
Req-111 |  |  |  | Develop UI Interface for Exploratory Data Analysis | Completed | Chanabasagouda PATIL
Req-112 |  |  |  | Develop UI Interface for Data Profiling | Completed | Chanabasagouda PATIL
Req-113 |  |  |  | Develop UI Interface for Aspects Generation | Completed | Chanabasagouda PATIL
Req-114 |  |  |  | Develop UI Interface for Sentiment Analysis | Completed | Chanabasagouda PATIL
Req-115 |  | Flask App Development | Backend Development | Create the Python Falsk App for interaction with UI | Completed | Chanabasagouda PATIL
Req-116 |  |  |  | Develop Flask Interface for Preliminary Analysis | Completed | Chanabasagouda PATIL
Req-117 |  |  |  | Develop Flask Interface for Detailed Analysis | Completed | Chanabasagouda PATIL
Req-118 |  |  |  | Develop Flask Interface for Exploratory Data Analysis | Completed | Chanabasagouda PATIL
Req-119 |  |  |  | Develop Flask Interface for Data Profiling | Completed | Chanabasagouda PATIL
Req-120 |  |  |  | Develop Flask Interface for Aspects Generation | Completed | Chanabasagouda PATIL
Req-121 |  |  |  | Develop Flask Interface for Sentiment Analysis | Completed | Chanabasagouda PATIL
Req-122 |  | AI Module Development | AI Development | Develop AI Module to generste dynamic report for Preliminary Analysis | Completed | Chanabasagouda PATIL
Req-123 |  |  |  | Develop AI Module to generste dynamic report for Detailed Analysis | Completed | Jayachandra KODALI
Req-124 |  |  |  | Develop AI Module to generste dynamic report for Exploratory Data Analysis | Completed | Jayachandra KODALI
Req-125 |  |  |  | Develop AI Module to generste dynamic report for Data Profiling | Completed | Chanabasagouda PATIL
Req-126 |  |  |  | Develop AI Module to generste dynamic report for Aspects Generation | Completed | Chanabasagouda PATIL
Req-127 |  |  |  | Develop AI Module to generste dynamic report for Sentiment Analysis | Completed | Madhav SriMohan
Req-128 |  | Unit Testing | Unit Testing | Perform Unit Testing and prepare Unit Testnig doc for Preliminary Analysis | Completed | Chanabasagouda PATIL
Req-129 |  |  |  | Perform Unit Testing and prepare Unit Testnig doc for Detailed Analysis | Completed | Chanabasagouda PATIL
Req-130 |  |  |  | Perform Unit Testing and prepare Unit Testnig doc Exploratory Data Analysis | Completed | Chanabasagouda PATIL
Req-131 |  |  |  | Perform Unit Testing and prepare Unit Testnig doc for Data Profiling | Completed | Chanabasagouda PATIL
Req-132 |  |  |  | Perform Unit Testing and prepare Unit Testnig doc for Aspects Generation | Completed | Chanabasagouda PATIL
Req-133 |  |  |  | Perform Unit Testing and prepare Unit Testnig doc for Sentiment Analysis | Completed | Madhav SriMohan
Req-134 | Manual Testing | UI Testing (Functional) | Perform Functionlity Testing for UI | Perform Functionlity Testing for UI and Testnig doc for Preliminary Analysis | Completed | Tejaswi
Req-135 |  |  |  | Perform Functionlity Testing for UI and Testnig doc for Detailed Analysis | Completed | Tejaswi
Req-136 |  |  |  | Perform Functionlity Testing for UI and Testnig doc Exploratory Data Analysis | Completed | Tejaswi
Req-137 |  |  |  | Perform Functionlity Testing for UI and Testnig doc for Data Profiling | Completed | Tejaswi
Req-138 |  |  |  | Perform Functionlity Testing for UI and Testnig doc for Aspects Generation | Completed | Tejaswi
Req-139 |  |  |  | Perform Functionlity Testing for UI and Testnig doc for Sentiment Analysis | Completed | Tejaswi